## Hospitals
Hospital Name | Draft Plan Process | Next Step | Engagement | Plan Status | Plan | Grants | Regional Meeting Updates - concerns and gaps | Initial Meetings | Primary Focus From Grant App | Leaders | Location | Region | Contact Name | Contact Email | Grant Status | CAH/PPS | Engages in AHS work | Form W-9 included | Employee time (15% overhead threshold) (Y/N) | Vendor (Y/N) | Start-up (Y/N) | Grant Decision Detail
Gifford Hopsital | Erin | Schedule meeting soon to review plan, ask to meet with Bratt | OK | Submitted draft 1/15/26 | Good | Fully executed |  |  | Consulting services for planning + shared radiology | Michael Costa | Randolph | Central |  |  | Awarded | [6 empty] | yes
Northwestern Medical Center (NMC) | Erin | Schedule soon | Good | Submitted draft 1/15/26 | OK | In process with BO | Birthing, Oncology. Shares cardiologist with Copley | Monday 11/17 | Innovative approach to maintain birthing | Jonathan Billings | St. Albans | Northwest |  |  | Awarded | [6 empty] | Questions on value of spending money on campaigns.
Mount Ascutney | Katie | Schedule soon discuss willingness to meet with other hospitals | Not Good | Extension to 2/1 | FU Friday | In process with BO | Dr. Schneider CMO - surgery |  | Age Friendly Program, center of excellence for Aging | Matt Foster | Windsor | Southeast |  |  | Awarded | [6 empty] | Need more detail on overall plan
Rutland Regional Medical Center (RRMC) | Katie | Schedule meeting asap: plan review with prioritization, hospice project review and ability to contribute to statewide conversation, ability to support Bratt, HUB | OK | Submitted draft 1/15/26 | Good | In process with BO | Derm in community | Monday 11/17 | Improving hospice utilization for patients with advanced illness in Rutland County through earlier palliative care integration and coordinated cross-setting workflows. | Judi Fox | Rutland | Southwest |  |  | Awarded | [6 empty] | yes
Southwestern Vermont Medical Center (SVMC) | Katie | Schedule asap to walk through plan and get to better spot, talk about grant work | Good | Submitted draft 1/15/26 | Need Follow up | In process with BO |  |  | RN Bridge to PCP program | Estavan Garcia | Bennington | Southwest |  |  | Awarded | [6 empty] | Need to ask for more detail on project and intended impact.
UVMMC | Erin |  | OK | Submitted draft 1/15/26 | Good | Not eligible |  |  | Not eligible for grant | Steve Leffler |  | Northwest |  |  | Na
Springfield Hospital | Erin | Schedule asap, grants, mh, DAIL | OK | Extension to 2/15 |  | Not yet approved | Relationship with Northstar Health is interesting. Oncology and cardiology are big concerns | Thusday 11/13 | Feasibility study for clinical services redesign - consulting service | Bob Adcock | Springfield | Southeast |  |  | Needs Follow Up | [6 empty] | Team concerns need to be defined
North Country Hospital | Erin | Meet with them soon to review plan/ fu on vendor | Good | Submitted draft 1/14/26 | Good | Waiting on budget from hospital | Pulmonology, Tele-Neonatology (successful), SUD outside of hospital, really relevant in this case |  | Partner with NVRH to pay a PM, subject matter experts and legal cousel to support regionalization efforts. | Tom Frank | Newport | Northeast |  |  | Awarded | [6 empty] | yes
Northeastern Vermont Regional Hospital (NVRH) | Erin | Meet with them soon to review plan/ fu on vendor | Good | Submitted draft 1/14/26 | Good | Waiting on budget from hospital | Cardiology, Tele-ICU |  | Partner with North Country to pay a PM, subject matter experts and legal cousel to support regionalization efforts. | Shawn Tester | St. Johnsbury | Northeast |  |  | Awarded | [6 empty] | yes
Brattleboro Memorial Hospital (BMH) | Erin | Schedule meeting asap: plan review with prioritization, birthing, oncology, grant | OK | Submitted draft 1/15/26 | Good | Waiting on budget from hospital | Urology, Maintaining births and onc | Thursday 11/20 | Resources to create their plan and assess service lines | Elizabeth McCLarney, Toni Blofson | Brattleboro | Southeast |  |  | Awarded | [6 empty] | yes
Central Vermont Medical Center (CVMC) | Erin |  | OK | Submitted draft 1/15/26 | Good | Waiting on hospital signature |  |  | Technology solutions to acuity management and transfers | Anna Noonan | Berlin | Central |  |  | Awarded | [6 empty] | yes
Porter Hospital | Erin |  | OK | Submitted draft 1/15/26 | Good | Waiting on hospital signature |  |  | Technology solutions to acuity management and transfers | Bob Ortmyer | Middlebury | Central |  |  | Awarded | [6 empty] | yes
Copley Hospital | Katie | Schedule soon | Not Good | Extension to 2/1 | FU Tomorrow/Alex Braaten | Waiting on Kristin McClure signature |  |  | Consulting services - KH | Joe Woodin | Morrisville | Central |  |  | Awarded | [6 empty] | Concerns about sustainability of the change to be discussed
Grace Cottage Hospital | Katie | Schedule soon | Good | Extension to 2/1 | Good | Waiting on Kristin McClure signature | Derm in community | Friday 11/7 | Decrease burden on regional acute care centers and ED through Swing Bed Program and ED shift to same day initiative | Oliva Sweetnam | Townshend | Southeast |  |  | Awarded | [6 empty] | Question on using money for marketing

## Sheet2 (hidden)
Not Good
OK
Good
Really Good