## Slide 1
The Six-Pillar Execution Sequence
Revised sequence: Policy → Technology → Economics → Clinical → Equity → Operations
1
2
3
4
5
6
Policy
Is it permissible?
Establish enforceable authority, mandate participation, and secure transformation capital
Mandatory architecture + Policy-driven capital (RHT award) that funds the tech build
Technology
Is it possible?
Build integrated clinical + claims data infrastructure BEFORE financial risk is assumed
Operating system for Economics, Clinical & Operations — must exist before global budgets go live
Economics
Is it sustainable?
Deploy global budgets and reference-based pricing onto a system that can already see itself
Incentive architecture goes live only when technology can support it — design happens in parallel during Stage 2
Clinical
Is it effective?
Redesign care delivery and transform clinical practice on aligned incentives
ROI realized only when payment incentives are live and technology can identify which patients need what
Equity
Is it just?
Audit, calibrate and correct — including social risk adjustment embedded in payment design
Constraining dependency: must be embedded in Stages 3–4 and audited here against real population data
Operations
Is it executable?
Close the administrative cost gap and translate strategy into implemented programs
Execution layer: optimizes a system already defined by Stages 1–5. Vermont gap: $1,303/discharge vs. national benchmark

## Slide 2
Vermont Evidence & OneCare Sequencing Failures
Vermont anchors show what correct sequencing achieves. OneCare failures show what happens when foundational stages are skipped.
1
2
3
4
5
6
Policy
Vermont anchor
Acts 167, 51 & 68
AHEAD Model federal agreement
$195M Rural Health Transformation award
Mandatory provider reporting requirements
Technology
Vermont anchor
VHCURES all-payer claims database
VITL/VHIE clinical data exchange
AHS-GMCB Analytics Vendor
AI-assisted documentation & RPM
Economics
Vermont anchor
Global hospital budgets
Reference-Based Pricing at ≤200% Medicare
AHEAD EAST Fund up to $150M/year
Total Cost of Care model activation
Clinical
Vermont anchor
PCMH transformation
Collaborative Care Model (CoCM)
CCBHC expansion
Blueprint 5.8:1 ROI from primary care
Equity
Vermont anchor
HRSN screening at scale
EAST Fund for social determinants
Social risk adjustment in global budgets
Rural Emergency Hospital model
Operations
Vermont anchor
Rural Health Redesign Center (RHRC)
Shared administrative services
14-hospital transformation planning
Community Health Teams
OneCare failure
Stage 1 — Policy: Optional participation — no policy foundation to enforce accountability. High-cost providers opted out, leaving OneCare unable to control total cost.
Stage 2 — Technology: No integrated, real-time clinical and claims data. Care managers worked from data 60–90 days old — the 'Managing Blind' failure mode.
Stage 3 — Economics: Payment model launched before technology substrate was ready. Economics-as-management attempted while managing blind — producing unexpected financial losses.